PSIA LMP Engagement Project

Draft Communications Strategy

Updated August 29, 2022

| Strategy Element | Communications Strategy & Tactics |
| --- | --- |
| Project Purpose | - The purpose of this Project is to engage with stakeholders and First Nations with an interest in the seaweed sector in BC to identify in-demand skills, career paths into and within the sector, transferrable skills from other sectors, skills training requirements and implications for recruitment and retention to support the continued development of the BC seaweed sector. |
| Key Communication Goals | - Ensure relevant stakeholders, First Nations and government agencies are aware of the project and its value proposition and have opportunities to participate - Generate interest and strong support for the project and next steps among key stakeholders and First Nations - Attract key interested stakeholders and First Nations representatives to commit to participating on the project Governance Committee |
| Communication Objectives | - Plan and implement a diverse and inclusive sector engagement process focusing on the sector’s current and future workforce and labour market gaps, challenges and necessary strategies - Effectively implement a sector engagement process that obtains stakeholder and First Nations’ insights, experiences and clear answers to key engagement questions - The engagement leads to the creation of a strong, diversity and interested Governance Committee membership - Engagement process outputs directly inform the sector’s road ahead including a proposal for future LMP phases to develop and implement a sector long term workforce strategy which also addresses shorter term priorities |
| Target Audiences **specific organizations/contacts to be added during detailed Engagement planning** | Stakeholders - PSIA members (42) (since “internal, notice of Project can be made to members before communication approvals - Relevant industry associations (e.g., BC Salmon Farmers, Canada Aquaculture Industry Alliance, Vancouver Island Economic Alliance, etc.) - Sector suppliers and other parts of sector supply chain (some are part of PSIA membership) Government agencies - Federal – Agriculture & Agri-Food Canada, Fisheries, ESDC - Provincial – Agriculture, JERI, MAEST - Municipal/local (i.e., a few regional districts or UBCM) Education, Training and Employment Service Providers - Officials in K-12 school districts (i.e., a few coastal School Districts) - Post-secondary (public and private) (e.g., North Island College) - Employment programs and services (e.g., North Island Employment Foundations Society) Indigenous Organizations - 14 First Nation communities in the Indigenous partners network - 4 other First Nations - 21 First Nations communities under the Pacific Integrated Commercial Fisheries Initiative - First Nations Fisheries Council Agriculture Coordinating Committee (5 First Nations) - Other Indigenous organizations (to be determined) Others - To be determined |
| Geographic Scope | - Stakeholders and First Nations mainly in Vancouver Island, Mainland Mid-Coast and Mainland North Coast |
| Key Messages *unique messaging will be developed for specific target audiences, particularly businesses, First Nations and education and training organizations | - The sector represents key potential economic, social, community and environmental benefits to British Columbians, particularly in coastal and rural communities - The sector will be an increasingly important part of Canada’s Blue Economy Strategy as we better understand the level of CO2 reduction resulting from kelp opportunities. - As the sector gains a foothold and expands, significant workforce and entrepreneurial opportunities will grow - The sector is a hidden gem for BC and Canada and this project will help it gain traction and momentum in becoming known and recognized as an opportunity by British Columbians, businesses, communities, First Nations and the media - First Nations will play an increasing central role in the development and growth of the sector |
| Internal Communication Protocol | - Ensure clear, regular and optimal communication between: - PSIA and Working Group - PSIA and Working Group and Project Manager - PSIA, Project Manager and MAEST contact - PSIA and Project Manager and external organizations |
| Communication Channels | What/Who - PSIA and members - Other industry associations (also see Target Audiences) - First Nations and Indigenous networks (associations) - Education, post-secondary education and employment and training provider networks (associations) - Local, regional and provincial media outlets - Government agencies How - News releases (e.g., Project launch and later) - PSIA social media and direct email messages - Virtual meetings with organizations as needed (August, September) - Meetings, conferences (e.g., Vancouver Island Economic Alliance October 26-27, 2022) already planned |
| Engagement Activities **more fully defined in the Project Work Plan and a Project Engagement Plan for late July/August** | - Awareness-building about the project and sector through direct messaging and social media - Survey of stakeholders, First Nations and government agencies - Ten interviews of key informants on the sector - Validation of findings through two focus groups of stakeholders and First Nations - Confirmation of stakeholders and First Nations to join the Governance Committee - Distribution and promotion of final report (subject to any necessary MAEST approval |
| Communication Materials | - Cover email and Project Backgrounder - News release (one for launch, one for final report and announcement of Governance Committee) – subject to Province prior approval - Social media post content - Slide deck(s) for launch, meetings, engagement, summaries of outputs, etc. - Engagement materials (invitations, instruments, etc.) |
| Timelines | - June 1 – Draft and submit Communication Strategy - Completed - June 10 or earlier if possible – Approval (may be up to two weeks (June 24) - Approved - After approval – Formal project launch (news release and backgrounder) and implementation of project engagement – Project launched and news release issued July 4 with the online survey - Subject to approval – Preparation of communication materials – initial materials completed - June 20 – Start messaging with start of engagement via social media, events, etc. (internal audience only until approval) - Completed - July 4-August 31 – Complete engagement – Complete launch and survey - September – Draft and finalize report and outreach to create Governance Committee - Late October – Final report event - Late October through November – Feedback & approvals by MAEST/SLMP and MAEST/GCPE |
| Communication Approval Requests | - Approval of launch news release - Approved - Approval of final report, Governance Committee announcement and report distribution by MAEST/SLMP and MAEST/GCPE |
| Implementation of Communication Strategy including the Engagement process | - To be defined in the (rolling) Project Work Plan and detailed Engagement planning |